## Sheet1
Task | Estimation (hours) | Priority (1-5) | Sprint When Finished
Set up MongoDB and user accounts | 3 | 5 | 1
Install Node.js and MongoDB drivers | 2 | 5 | 1
Create MongoDB connection program | 4 | 5 | 1
Create MongoDB document add operation | 3 | 4 | 1
Create MongoDB document read operation | 3 | 4 | 1
Create MongoDB document update operation | 3 | 4 | 1
Create MongoDB document delete operation | 3 | 4 | 1
Create server startup program | 4 | 3 | 1
Refactor existing files to work with new server startup program | 4 | 3 | 1
Create basic html webpage skeleton | 2 | 2 | 1
Implement http request handlers server-side | 5 | 5 | 1
Create POST request in basic webpage | 4 | 3 | 1
Create html page and POST request for MongoDB document add operation | 4 | 4 | 1
Create html page and POST request for MongoDB document read operation | 4 | 4 | 1
Create html page and POST request for MongoDB document update operation | 5 | 4 | 1
Create html page and POST request for MongoDB document delete operation | 4 | 4 | 1
Update web page structure and navigation | 6 | 1 | 2
Refactor server-side http request handler logic | 4 | 2 | 2
Implement current html skeleton with CSS elements | 8 | 3 | 2
Secure connection string with .env file | 2 | 1 | 2
Implement security error handling | 14 | 2 | 2
Determine non-static hosting location for server | 6 | 2 | 2
Determine user login solution (DUO/myBama or in-house) | 10 | 3 | 3
Implement user-login functions and handlers | 20 | 5 | 3
Create user login page | 3 | 5 | 3
Create user management pages | 4 | 4 | 3
Implement security measures for user login data | 15 | 3 | Backlog
Create html page with checkout interface | 6 | 4 | 2
Create POST requests to handle checkout operations | 10 | 4 | 2
Determine solution for email features (reminders and approval requests) | 4 | 2 | Backlog
Update update parts page to form version | 8 | 1 | Backlog
Add data validation for web input fields | 12 | 2 | 2
Update server-side handlers for checkout | 12 | 4 | 2
Add server-side data validation for checkout | 4 | 3 | 2
Update user alerts popups | 3 | 2 | 2
Add html outline for equipment return | 5 | 4 | 3
Create request handlers for equipment return | 8 | 4 | 3
Add styling for equipment return | 3 | 2 | 3
Implement e-mail server / API | 16 | 4 | Backlog
Write e-mail logic for requests and notifications | 12 | 3 | Backlog
Create user profile (currently checked out items) | 14 | 2 | 3
Implement user profile table population and username handlers | 12 | 2 | 3
Refactor styling and page formatting | 6 | 1 | 3
Configure hosting solution | 30 | 5 | 3
Write testing suite for user input | 6 | 2 | 3
Implement dynamic nav bar population | 10 | 3 | Backlog
Augment data validation for add and update pages | 8 | 1 | Backlog
Documentation and Readme work | 18 | 4 | 3
Configure npm-related security concerns | 15 | 2 | Backlog