## Slide 1: Robotics Lab Inventory
Owen Campbell, Preston Mazzei, Adam Wrote, Blake Cantrell

## Slide 2: Project Focus
Currently, the Robotics Lab has sub-optimal inventory management, where the lab equipment and materials are not tracked properly.
Our job is to build a web application to help the Robotics Lab manage inventory
The web app will allow users to add, update, remove, and read lab equipment. It will also allow users to check out this equipment and notify users when it is due back.

## Slide 3: Sprint 1 Goal
The goal for this sprint was to get all the basic functions working
  MongoDB
  Basic website
  Add, update, remove, and read options
  Full pipeline functionality (web->server->DB)

## Slide 4: Major Sprint Achievements
Our database is set up
We have a basic website set up
  The pages that are set up are mostly for testing; we have plans to improve them greatly
All server-side processes have been established
  We'll need to do further testing to transform generic processes (CRUD, request handling, etc.)to actual use cases

## Slide 5: Project / Sprint Backlog
Task | Date Started | Date Completed | Priority
Set up MongoDB and Install all workflow tools | 2/7/2024 | 2/8/2024 | Sprint 1
Program Node.js DB operations | 2/9/2024 | 2/12/2024 | Sprint 1
Create html skeleton | 2/12/2024 | 2/22/2024 | Sprint 1
Program http request pipeline | 2/20/2024 | 2/26/2024 | Sprint 1
Refactor DB operations to be modular | 2/13/2024 | 2/20/2024 | Sprint 1

## Slide 6: Project / Sprint Backlog (cont.)
Task | Date Started | Date Completed | Priority
Refactor after http request implementation | 2/27/2024 | - | Sprint 2
Set up login data | - | - | Sprint 3
Populate DB with lab parts | 2/16/2024 | - | Ongoing
Store connection data in .env files | - | - | Sprint 3
Update webpage structure | - | - | Sprint 2
Refactor server-side request handler | - | - | Sprint 2

## Slide 7: What was not completed / Lessons
Incomplete documentation and maintenance of run instructions
  Proper upkeep of this allows for better communication between team members and the cybersecurity specialists
Room for improvement with versioning practices
  Some feature implementations could have used more than one branch to enable better organization and efficiency

## Slide 8: Demo (2-3min)
Time permitting

## Slide 9: Questions?